## Schedules
PROJECT SCHEDULE
Builder
Project Address:
Permit date
Direction: Fill in the start date and duration (shaded blue). The end date will autopopulate based on working days.
Title | Start | Dur. |  | End | Actual Start | Actual End
Site Work
Abatement / Demo |  |  | -1
Excavation / Shoring / Utilities |  |  | -1
Foundation |  |  | -1
Backfill/Utilies |  |  | -1
Vertical - Exterior
Framing / Window Install / Roof |  |  | -1
Siding |  |  | -1
Exterior Paint |  |  | -1
Landscape/Hardscapes |  |  | -1
Interior
MEPs Roughin |  |  | -1
Insulation/Drywall |  |  | -1
Cabinets/Tile/ Countertops/Millwork |  |  | -1
Interior Paint |  |  | -1
MEP Trim |  |  | -1
Touchups |  |  | -1
Final Clean |  |  | -1
Finale
To Market |  |  | -1
| DURATION |  |  |  | Days
Months
Formulas:
End = IFERROR(WORKDAY([Start],E12),"")

## sample
PROJECT SCHEDULE
Builder
Project Address:
Permit date
Direction: Fill in the start date and duration (shaded blue). The end date will autopopulate based on working days.
Title | Start | Dur. |  | End | Actual Start | Actual End
Site Work
Abatement / Demo | 2022-12-01 | 1 | 0 | 2022-12-01
Excavation / Shoring / Utilities | 2022-12-05 | 5 | 4 | 2022-12-09
Foundation | 2022-12-12 | 13 | 12 | 2022-12-28
Backfill/Utilies | 2022-12-29 | 12 | 11 | 2023-01-13
Vertical - Exterior
Framing / Window Install / Roof | 2023-01-16 | 40 | 39 | 2023-03-10
Siding | 2023-03-11 | 10 | 9 | 2023-03-23
Exterior Paint | 2023-03-25 | 5 | 4 | 2023-03-30
Landscape/Hardscapes | 2023-06-15 | 15 | 14 | 2023-07-05
Interior
MEPs Roughin | 2023-03-10 | 30 | 29 | 2023-04-20
Insulation/Drywall | 2023-04-21 | 15 | 14 | 2023-05-11
Cabinets/Tile/ Countertops/Millwork | 2023-05-12 | 21 | 20 | 2023-06-09
Interior Paint | 2023-06-10 | 5 | 4 | 2023-06-15
MEP Trim | 2023-06-17 | 12 | 11 | 2023-07-03
Touchups | 2023-07-05 | 3 | 2 | 2023-07-07
Final Clean | 2023-07-07 | 2 | 1 | 2023-07-10
Finale
To Market | 2023-07-10 |  | -1 | 2023-07-07
| DURATION |  |  | 221 | Days
|  |  |  | 7.3667 | Months
Formulas:
End = IFERROR(WORKDAY([Start],E12),"")